## Daily status
Associate Name | Region | Category | Model Name | 2023-02-20
Category
Deepashri | SA | Diapers | Active Baby | Adding new media variables to the model datacube Will add base variables into the model for Active Baby after QC the final model datacube
Deepashri | SA | Diapers | New Born Baby
Deepashri | SA | Diapers | Dry Comfort
Kavya | SA | Diapers | Gold | Adding "Total Huggies" Media variables to model datacube Will add base variables into the model for Gold after QC the final model datacube
Kavya | SA | Diapers | Gold Pants and slipons
Kavya | UK | Facial Tissue | Kleenex
Kavya | UK | Diapers | Dry nites - Pajama Pants | Will share DRD for the brand Drynites
Khyati | UK | Toilet Tissue | Andrex - Premium | Currently comparing the 2021 data with the old project file/ We will start working on Andrex DRD
Khyati | UK | Toilet Tissue | Andrex - Mainline
Khyati | UK | Toilet Tissue | Andrex - Moist

## Project Tracker
S No | Associate Name | Region | Category | Model Name | Step 1 | Step 2 |  |  |  | Step 3 | Step 4 | Step 5 | Step 6 | Step 7 | Step 8 | Step 9 | Step 10 | Step 11 | Comments
|  |  | Category |  | Kick-off & Scoping | Data Collection | Volumetric Data | Media Data | Shipment and Financial Data | Data Review & Preparation* | Data Confirmation from Client | Pre Model Diagnostics | Modeling | Review Analysis & Insights | Topline Presentation & Feedback | Simulations and Optimizations | Deep Dive Models | Final Presentation
1 | Deepashri | SA | Diapers | Active Baby
2 | Deepashri | SA | Diapers | New Born Baby |  |  |  | Media query
3 | Deepashri | SA | Diapers | Dry Comfort |  |  |  | Media query |  | Need to Include Total Huggies level Media data
4 | Kavya | SA | Diapers | Gold
5 | Kavya | SA | Diapers | Gold Pants
6 | Kavya | UK | Facial Tissue | Kleenex
7 | Khyati | UK | Diapers | Dry nites - Pajama Pants
8 | Khyati | UK | Toilet Tissue | Andrex - Premium
9 | Khyati | UK | Toilet Tissue | Andrex - Mainline
10 | Khyati | UK | Toilet Tissue | Andrex - Moist
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Waiting for Extra care media confirmation

## Utilization Deepashri
Activities | WEEK 6 |  |  |  | WEEK 7 |  |  |  | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19
| 2023-01-02 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 2023-01-09 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03
Resource Utilization | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kick-off & Scoping
Data Collection
Data Review & Preparation*
Pre Model Diagnostics
Modeling
Review Analysis & Insights
Topline Presentation & Feedback
Simulations and Optimizations
Deep Dive Models
Final Presentation
SME
PM

## Utilization Kavya
Activities | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19
| 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03
Resource Utilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kick-off & Scoping
Data Collection
Data Review & Preparation*
Pre Model Diagnostics
Modeling
Review Analysis & Insights
Topline Presentation & Feedback
Simulations and Optimizations
Deep Dive Models
Final Presentation
SME
PM

## Utilization Khyati
Activities | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19
| 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03
Resource Utilization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kick-off & Scoping
Data Collection
Data Review & Preparation*
Pre Model Diagnostics
Modeling
Review Analysis & Insights
Topline Presentation & Feedback
Simulations and Optimizations
Deep Dive Models
Final Presentation
SME
PM