## Game
|  |  |  | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05
项目名称 | 项目范围 | 第1周 | 第2周 | 第3周 | 第4周 | 第5周 | 第6周 | 第7周 | 第8周 | 第9周 | 第10周 | 第11周 | 第12周 | 第13周 | 第14周
Bandai Namco |  |  |  | 2022-09-26: KO; 2022-10-03: DRD; 2022-10-10: TR1; 2022-11-07: PI1; 2022-12-05: TR2
Fotoable - 3KPIs | 三个模型+ SaaS (平台) | 9月8日 KO |  | 9月21日 (三个KPI的数据收集) |  | 10月1日-10月7日 国庆休息 | DRD |  | Diwali 排灯节 |  | PI （2个KPI） | PI (1个KPI) |  | FIN | Dashboard结果呈现
KO | 项目启动
DR | 数据收集
DRD | 数据回顾(Excel)
TR | Fit, ROI, contribution, due-tos
PI | 初步结果(Excel)
FIN | 最终报告(响应曲线)

## Game (2) (hidden)
| SCOPE | 2022-09-08 | 2022-09-15 | 2022-09-22 | 2022-09-29 | 2022-10-06 | 2022-10-13 | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-11-10 | 2022-11-17 | 2022-11-24 | 2022-12-01 | 2022-12-08 | 2022-12-15 | 2022-12-22 | 2022-12-29 | 2023-01-05 | 2023-01-12 | 2023-01-19 | 2023-01-26 | 2023-02-02
PROJECT | Scope | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22
Kick-off | bar: 2022-09-08
Data Received | bar: 2022-09-22
Data Review (Excel) | bar: 2022-10-06
KPI #1 | Prelim Insights (Excel) | bar: 2022-10-27
Final Insights Deck (incl Response curves) | bar: 2022-11-10
| Model walkthrough | 2022-11-24: Model WT
KPI #2 | Prelim Insights (Excel) | bar: 2022-12-01
Final Insights Deck (incl Response curves) | bar: 2022-12-15
| Model walkthrough | 2022-12-29: Model WT
KPI #3 | Prelim Insights (Excel) | bar: 2023-01-05
Final Insights Deck (incl Response curves) | bar: 2023-01-19
| Model walkthrough | 2023-02-02: Model WT