## Timeline
STONE Proposed Timelines
Stages | Week Starting
|  | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31
Project Spec & Kick off | Kick Off Meeting
Data Collection Completion | bar: 2022-06-13
Data Prep and Review |  | 2022-07-11: Data Review Deck
Modelling - Model - 1 (Auto Cred) | bar: 2022-07-18 to 2022-08-01
Prelim Results - Model - 1 (Auto Cred) (Fits, Media Contributions, ROI & Effectiveness) |  | 2022-08-08: Topline results
Modelling - Model - 2 (Inbound) | bar: 2022-07-18 to 2022-08-01
Prelim Results - Model - 2 (Inbound) (Fits, Media Contributions, ROI & Effectiveness) |  | 2022-08-08: Topline results
Modelling - Model - 3 (Polo) | bar: 2022-08-08 to 2022-08-22
Prelim Results - Model - 3 (Polo) (Fits, Media Contributions, ROI & Effectiveness) |  | 2022-08-29: Topline results
Modelling - Model - 4 (Renda Extra) | bar: 2022-08-08 to 2022-08-22
Prelim Results - Model - 4 (Renda Extra) (Fits, Media Contributions, ROI & Effectiveness) |  | 2022-08-29: Topline results
Response Curves (3 Models) (AutoCred, Inbound & Polo)** |  | 2022-09-19: Response curves
Simulation setup (3 Models) (AutoCred, Inbound & Polo)** | bar: 2022-08-08 to 2022-10-31
Final insights presentation (incl results, Response curves & optimizations) |  | 2022-10-17: Final Insights Deck
Brilliant Basics data collection + Data prep | bar: 2022-09-19; 2022-10-03 to 2022-10-17
Brilliant Basics data review |  | 2022-10-10: Facebook BB Data review
Brilliant Basics deep dives | bar: 2022-10-10 to 2022-10-17; 2022-10-31
Brilliant Basics deep dive Results |  | 2022-10-24: Facebook BB results
Note:
1). **= Response curves and simulation for "Renda Extra" excluded (no direct media execution)
2). Any follow-ups or additional request after the top-line results will result in a change in subsequent timeline

## Timeline Mixed Effects
STONE Proposed Timelines
Stages | Week Starting
|  | 2022-06-13 | 2022-06-20 | 2022-06-27 | 4th/July - 25th/July | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21
Project Spec & Kick off | Kick Off Meeting
Data Collection Completion
Data Prep and Review | [5 empty] | 2022-08-01: Data Review Deck
Modelling - Model - 1 (Auto Cred) | bar: 2022-08-08 to 2022-08-29
Prelim Results - Model - 1 (Auto Cred) (Fits, Media Contributions, ROI & Effectiveness) | [5 empty] | 2022-09-05: Topline results
Response Curves | [5 empty] | 2022-09-26: Response curves
Simulation setup | bar: 2022-08-29 to 2022-10-17; 2022-10-31 to 2022-11-21
Final insights presentation (incl results, Response curves & optimizations) | [5 empty] | 2022-10-24: Final Insights Deck
Brilliant Basics data collection + Data prep | bar: 2022-09-26; 2022-10-24 to 2022-11-07
Brilliant Basics data review | [5 empty] | 2022-10-17: Facebook BB Data review
Brilliant Basics deep dives | bar: 2022-10-24; 2022-11-07; 2022-11-21
Brilliant Basics deep dive Results | [5 empty] | 2022-10-31: Facebook BB results
Note:
1). Any follow-ups or additional request after the top-line results will result in a change in subsequent timeline

## Sheet1
| 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23
Timelies | 2022-08-01: Data Review Deck; 2022-08-08: Modelling; 2022-08-15: Data Review Deck; 2022-08-22: Modelling; 2022-08-29: Modelling; 2022-09-05: Modelling; 2022-09-12: Modelling; 2022-09-19: Modelling; 2022-09-26: Topline results & Response curves; 2022-10-24: Final Insights Deck
Secondary Analysis Timeline | 2022-10-17: Facebook BB Data review; 2022-10-31: Facebook BB results; 2022-11-28: Final Insights Deck
Actual delivery | 2022-08-08: Data Review Deck; 2022-08-15: Data Review Deck V2; 2022-08-22: Modelling; 2022-08-29: Modelling; 2022-09-05: Modelling; 2022-09-12: Modelling; 2022-09-19: Modelling; 2022-09-26: Delivered Prelim results; 2022-10-03: Delivered Prelim results v4(FB Team); 2022-10-10: Delivered Prelim results v5; 2022-11-21: Response curves/simulation & Optimization/ Deepdive V1; 2022-12-19: Deepdive V2/Deepdive V3; 2022-12-26: Deepdive V4; 2023-01-23: Deepdive V5
Change Request | 2022-08-01: Delivered but there was a change request from Chris; 2022-08-08: Change request; 2022-08-22: Received revised data for FB and google; 2022-09-26: Change request from Chris; 2022-10-03: Change request from Chris; 2022-10-17: Started working on FB brilliant basics with existing data; 2022-10-24: waiting for the new data to receive; 2022-11-21: Change request from Chris; 2022-11-28: CS unavailability; 2022-12-05: CS unavailability; 2022-12-12: CS unavailability; 2022-12-19: Change request from Chris; 2023-01-23: Change request from Chris
Comments | 2022-08-15: Chris confirmed that the Final Presentation would be held in Nov last week due to the client's unavailability on the scheduled date.; 2022-11-21: Shared the deepdive results as per current data; 2022-11-28: Meeting set for this week in response to a client request; 2022-12-05: Waiting for the status update from Chris & new data to receive for deep dives