## Slide 1: DomClick
Project Status
Original Completion Date – 30th August 2021
Completion Date Based on Current Plan – 11th October 2021
Delay of - 5 weeks
Key points impacting timeline
Primarily impacted by delay in data collection (5 weeks)
Clarifications on TV data provided after first cut results (TV data was provided in 1000’s)
Model input specifications changed after first cut results (Use clicks instead of impressions for SEM and Mobile)
Model reviews took additional time on account of client being on vacation

## Slide 2: Bolt
Project Status
Original Completion Date – 19th July 2021
Completion Date Based on Current Plan – 30th Nov 2021
Delay of - 12 weeks
Key points impacting timeline
Primarily impacted by out of scope requests
  Creating detailed documentation on modelling process
  Creating out of sample validation and investigations on forecast accuracy - The holdout for additional period did not hold out well. Possible reasons could be environmental factors where economy is opening up, change in Promotional strategy – these are factors we need to explore
Data Clarifications and additional data added in ; additional data requested (to test promo variables) took further time to collect
Initial Model reviews were per timelines – model holdout worked well within the modelling data.

## Slide 3: Joom
Project Status
Original Completion Date – 4th October 2021
Completion Date Based on Current Plan – 25th October 2021
Delay of - 3 weeks
Key points impacting timeline
Primarily impacted by Data collection and clarifications
Change in the scope of the data ( Initially KPI included only Mobile Apps Revenue), Revenue from Websites have been included in the revised data)
Promotions and Media data for Website revenue were added in

## Slide 4: Unilever
Project Status
Original Completion Date – week of 6th September
Completion Date Based on Current Plan – week of 4th October
Delay of - 4 weeks
Key points impacting timeline
Data wrangling – Granularity of variables collected was much more than used in a typical MMM and had to be aggregated to make the data cube model ready.
Client was out on vacation for 3 weeks after initial training workshop.
Non-availability of good quality promotional data, aggregated national level data lead to additional 2 week delay as extra time was needed to iterate and figure out a best approach to use this data in the model.

## Slide 5: Domclick - Timelines
Tasks |  | 06/07 | 6/14 | 06/21 | 06/28 | 07/05 | 07/12 | 07/19 | 07/26 | 08/02 | 08/09 | 08/16 | 08/23 | 08/30 | 09/06 | 09/13 | 09/20 | 09/27 | 10/04 | 10/11 | 10/18
Data Collection | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Data Prep & Review | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Analysis - Phase 1 | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Analysis - Phase 2 | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Optimization and DDE Setup | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DDE Delivery | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Training | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Week

## Slide 6: Bolt - Timelines
Tasks |  | 05/10 | 05/17 | 05/24 | 05/31 | 06/07 | 06/14 | 06/21 | 06/28 | 07/05 | 07/12 | 07/19 | 07/26 | 08/02 | 08/09 | 08/16 | 08/23 | 08/30 | 09/06 | 09/13 | 09/20 | 09/27 | 10/04 | 10/11 | 10/18
Data Collection | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Data Prep & Review | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Analysis – Phase 1 | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Analysis – Phase 2 | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Insights Presentation | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Holdout validation/Promo Analysis/Additional Data requested
Week

## Slide 7: Joom - Timelines
Tasks |  | 08/02 | 08/09 | 08/16 | 08/23 | 08/30 | 09/06 | 09/13 | 09/20 | 09/27 | 10/04 | 10/11 | 10/18 | 10/25 | 11/01 | 11/08 | 11/15
Data Prep & Review | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Analysis (Modelling and Review) | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Optimization and Response Curves | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Insights Presentation | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DIY Support and Training | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Week

## Slide 8: Unilever - Timelines
Tasks |  | 05/24 | 05/31 | 06/07 | 06/14 | 06/21 | 06/28 | 07/05 | 07/12 | 07/19 | 07/26 | 08/02 | 08/09 | 08/16 | 08/23 | 08/30 | 09/06 | 09/13 | 09/20 | 09/27 | 10/04
Kick-off | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Training Workshop | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Data Collection | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Hands on Training | Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Actual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Client was on vacation
Week