## Sheet1
| 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23
Timelines(Finalised 9th Aug 2022) | 2022-08-01: Data Review Deck; 2022-08-08: Modelling; 2022-08-15: Data Review Deck; 2022-08-22: Modelling; 2022-08-29: Modelling; 2022-09-05: Modelling; 2022-09-12: Modelling; 2022-09-19: Modelling; 2022-09-26: Topline results & Response curves; 2022-10-24: Final Insights Deck
Secondary Analysis Timeline | 2022-10-17: Facebook BB Data review; 2022-10-31: Facebook BB results; 2022-11-28: Final Insights Deck
Actual delivery | 2022-08-08: Data Review Deck; 2022-08-15: Data Review Deck V2; 2022-08-22: Modelling; 2022-08-29: Modelling; 2022-09-05: Modelling; 2022-09-12: Modelling; 2022-09-19: Modelling; 2022-09-26: Delivered Prelim results; 2022-10-03: Delivered Prelim results v4(FB Team); 2022-10-10: Delivered Prelim results v5; 2022-11-21: Deepdive V1; 2022-12-19: Deepdive V2/Deepdive V3; 2022-12-26: Deepdive V4; 2023-01-23: Deepdive V5
Change Request | 2022-08-01: Delivered but there was a change request from Chris; 2022-08-08: Change request; 2022-08-22: Received revised data for FB and google; 2022-09-26: Change request from Chris; 2022-10-03: Change request from Chris; 2022-10-17: Started working on FB brilliant basics with existing data; 2022-10-24: Change request(waiting for the new data to receive); 2022-11-21: Change request from Chris; 2022-11-28: CS unavailability; 2022-12-05: CS unavailability; 2022-12-12: CS unavailability; 2022-12-19: Change request from Chris; 2023-01-23: Change request from Chris
Comments | 2022-08-15: Chris confirmed that the Final Presentation would be held in Nov last week due to the client's unavailability on the scheduled date.; 2022-11-21: Shared the deepdive results as per current data; 2022-11-28: Meeting set for this week in response to a client request; 2022-12-05: Waiting for the status update from Chris & new data to receive for deep dives