## Sheet1
File names | Data Received date | Delivery Date | /Description | Comments
Deepdive1 | 16th Nov 2022 | 23th Nov 2022 | Lower/Mid/Top split | Prior to this date, we were waiting for the complete data to receive
Deepdive2 | 12th Dec 2022 | 15th Dec 2022 | Change in request to Lower/Mid/Top for the latest file | change request
Deepdive3 |  | 20th Dec 2022 | Deepdives for Lower funnel splits(wo Dec-21 time period) | change request
Deepdive4 |  | 23rd Dec 2022 | Deepdives for Lower funnel splits(with Dec-21 time period) | change request
Deepdive5 |  | 29th Jan 2023 | Deepdives for Lower funnel splits with H1 vs H2(with Dec-21 time period) | change request
Notes: Model built till Nov 2021; If we include Dec-21 data , numbers won't match with the final presentation; this is communicated on 16th Dec 2022