## Reference
Red | Project Kick off | Yes | Abinash Pradhan | 1 Brand
Amber | Data Collection | No | Akash Iranna Ambiger | 3-Winter Brands (Hotpot,Knorr, & Soup Deli)
Green | Data Review |  | Akshay Johny | 6 Brands
| Data processing |  | Akshay Nandakumar Kundare | 6 Brands refresh
| Modeling |  | Ambili Balakrishnan | Aji-ngon (PNP & MMMM)
| Remodeling |  | Ankit Bansal | AUS_Fantastic_furniture_MMM_Mar_2022
| Reports |  | Anto Vaseekaran R. | BMW JP
| Simulation |  | Archak Majumder | Charlotte_Tilbury_MMM_August_2022
| Planning |  | Arnav Somani | CookDo
| Closed |  | Ashwin Sukumaran | FB - River Game - Top War AOS MMM Sep2022
|  |  | Avipsha Sengupta | FB_France_Luko_MMM_Sep_2022
|  |  | Blessy Joseph | FB_Freshly_Cosmetics_MMM_2022
|  |  | Bopanna B B | FB_Oechsle_Peru_1MMM_Feb2022
|  |  | Chandreyee Som | FB_Poland_Eobuwie_MMM_2022
|  |  | Deepashri Munishwar | Frozen Food 2 Brands
|  |  | Deepshikha Vijay | Frozen Food 2 Brands (Model Update)
|  |  | Dhanusha K | Fotoable
|  |  | Dhinakaran Raja Dakarapu | Headway_MMM_Aug_2022
|  |  | Divya Srivastav | HOTPOT
|  |  | Dwiref Desai | Jollibee
|  |  | G. Sateesh Reddy | Knorr
|  |  | Goutham Syamala | L'Oreal Kiehl's
|  |  | Gowtham P. Sabareesan | Mamaearth
|  |  | Gyan Deep | Melia
|  |  | Hardik Pathak | Nestle 2 brands Full MMM + BE models
|  |  | Harshita Saini | Nexon
|  |  | Harshitha Shankar | OLX Auto (2 Regions)
|  |  | I Jed Felix | Palsweet (Nov Update)
|  |  | Jagruti Khatri | PH_Globe_Sept2022
|  |  | Jaijo Johnson Mannpuram | Reduced Salt - 2 models
|  |  | Janarthanam M. | Rosdee & Birdee
|  |  | Jeevithaa S. | Soup Deli
|  |  | Joohi Rana | Stone
|  |  | Jyothsana M. Rao | Tenen
|  |  | Kamalakannan M | Topgames
|  |  | Karan Kumar Rijwani | Turkey_Hepsiburada_1MMM_July2022
|  |  | Karthik Grandhi | Umami & Dona Gusta
|  |  | Kartikaya Sahu | Umami Seasoning
|  |  | Kavya H Bhat | USA_FB_Pundit_1MMM_Nov2022
|  |  | Keerthana Sreenivasan | Kimberly Clart Australia Huggies
|  |  | Khyati Trivedi | Colgate_Columbia_12MMM_OralCare_April2022
|  |  | Lekha Janardhan | Colgate_Brazil_6MMM_June2022
|  |  | Manjeet Singh Rawat | Colgate_Philippines_4MMM_Sept2022
|  |  | Mansi Ashokkumar Choksi | Colgate_UK_4MMM_Nov2022
|  |  | Manthan Sanjay Buddhbhatti | Colgate_Israel_4MMM_Nov2022
|  |  | Mayank Agarwal | Mondelez_Chile_Oreo_MMMLite_Dec2022
|  |  | Mohammad Mohideen S | Colgate_Poland_OralCare_9MMM_Dec2022
|  |  | Mou Majumder | Mondelez_UAE_Oreo_MMM_Oct2022
|  |  | Muhammad Washif Ashraf | Kimberly Clark Australia UBK 2022
|  |  | Naveen Chhatwani | Brazil_Nivea_POC_Dec_2022
|  |  | Neeraj Choudhari | US_Mizkan_3MMM_2Penetration_Sept2021
|  |  | Neha Shaikh | TCCC -Ecom Phase 1 (55 Models)
|  |  | Nishant Yadav | TCCC -Ecom Phase 2 (40 Models)
|  |  | Nitin Wangnoo | Mondelez_UAE_CDM_MMM_July2022
|  |  | Palak Kumar | US_Mizkan_11Omnichannel_2023
|  |  | Palak Moolchand Jain | Kimberly_Clark_APAC(KCDEC22FTE)Kimberly-Clark
|  |  | Pourav Kumar Sahoo | KCC_EMEA_MMM_3FTE_Jan2023
Pramod Moolachery
Pratap Selvan Mudaliar
Pratheba Venkatesan
PRERANA H SULIBHAVI
Priyadharshni Gopinath
Rajavarman Venugopal
Rohan I Ail
Rujul Parekh
Sachin Kumar Pal
Sanjukta Ray
Santhosh Saran
Santosh Nair
Sashank Ramesh
Sekar Subramanian
Shaswat Mohapatra
Shilpa Shibu
Shreya Saluja
Shreyas Manjappa
Siddharth Kaithwas
Soham Girish Chandratre
Sravya Sri
Sri Balu
Srilakshmi Gannamaneni
Sudarsane G
Sumanta Singha Roy
Suresu Kumar
Tejasvita Saran
Umarfarookh Daval Nadaf
Vaibhav Dalakoti
Vaibhav Saraswat
Varsini A S
Vijay Ratnakar Dakarapu
Vikramaditya Mishra
Vincent Abraham
Yokesh Devaraj

## Projects & Resource Tracker
Week of → |  | 2023-02-13 |  |  |  |  | 2023-02-20 |  |  |  |  | 2023-02-27 |  |  |  |  | 2023-03-06
Working Hours |  | 40 |  |  |  |  | 47.5 |  |  |  |  | 47.5 |  |  |  |  | 47.5
Resource Name | Project Name | Activity | Hours Planned | Actual Hours | Leaves / Holidays | Bandwidth Availability / Delta | Activity | Hours Planned | Actual Hours | Leaves / Holidays | Bandwidth Availability / Delta | Activity | Hours Planned | Actual Hours | Leaves / Holidays | Bandwidth Availability / Delta | Activity | Hours Planned | Actual Hours | Leaves / Holidays | Bandwidth Availability / Delta
Abinash Pradhan
Abinash Pradhan
Abinash Pradhan
Akash Iranna Ambiger
Akash Iranna Ambiger
Akash Iranna Ambiger
Akshay Johny
Akshay Johny
Akshay Johny
Akshay Nandakumar Kundare | L'Oreal Kiehl's | Modeling | 16 |  |  |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 20
Akshay Nandakumar Kundare
Akshay Nandakumar Kundare
Ambili Balakrishnan
Ambili Balakrishnan
Ambili Balakrishnan
Ankit Bansal | Colgate_Israel_4MMM_Nov2022 | Data processing | 32 |  |  |  |  | 40 |  |  |  |  | 40 |  |  |  |  | 40
Ankit Bansal
Ankit Bansal
Anto Vaseekaran R.
Anto Vaseekaran R.
Anto Vaseekaran R.
Archak Majumder
Archak Majumder
Archak Majumder
Arnav Somani
Arnav Somani
Arnav Somani
Ashwin Sukumaran
Ashwin Sukumaran
Ashwin Sukumaran
Avipsha Sengupta | FB_Freshly_Cosmetics_MMM_2022 | Modeling | 32 |  |  |  |  | 40 |  |  |  |  | 40 |  |  |  |  | 40
Avipsha Sengupta
Avipsha Sengupta
Blessy Joseph | Colgate_Brazil_6MMM_June2022 | Modeling | 16 |  |  |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 20
Blessy Joseph
Blessy Joseph
Bopanna B B | Colgate_Philippines_4MMM_Sept2022 | Data processing | 25.6 |  |  |  |  | 32 |  |  |  |  | 32 |  |  |  |  | 32
Bopanna B B
Bopanna B B
Chandreyee Som | 6 Brands refresh | Data Collection | 16 |  |  |  |  | 20
Chandreyee Som | HOTPOT | Project Kick off | 16 |  |  |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 20
Chandreyee Som
Deepashri Munishwar | KCC_EMEA_MMM_3FTE_Jan2023
Deepashri Munishwar | KCC_EMEA_MMM_3FTE_Jan2023
Deepashri Munishwar | KCC_EMEA_MMM_3FTE_Jan2023
Deepshikha Vijay
Deepshikha Vijay
Deepshikha Vijay
Dhanusha K | Kimberly_Clark_APAC(KCDEC22FTE)Kimberly-Clark | Data Review
Dhanusha K | Kimberly_Clark_APAC(KCDEC22FTE)Kimberly-Clark | Data processing
Dhanusha K | Kimberly_Clark_APAC(KCDEC22FTE)Kimberly-Clark | Modeling
Dhinakaran Raja Dakarapu
Dhinakaran Raja Dakarapu
Dhinakaran Raja Dakarapu
Divya Srivastav | FB_France_Luko_MMM_Sep_2022 | Modeling | 16 |  |  |  |  | 20
Divya Srivastav
Divya Srivastav
Dwiref Desai
Dwiref Desai
Dwiref Desai
G. Sateesh Reddy
G. Sateesh Reddy
G. Sateesh Reddy
Goutham Syamala
Goutham Syamala
Goutham Syamala
Gowtham P. Sabareesan
Gowtham P. Sabareesan
Gowtham P. Sabareesan
Gyan Deep
Gyan Deep
Gyan Deep
Hardik Pathak
Hardik Pathak
Hardik Pathak
Harshita Saini | Rosdee & Birdee | Data processing | 25.6 |  |  |  |  | 32 |  |  |  |  | 32 |  |  |  |  | 32
Harshita Saini | Frozen Food 2 Brands (Model Update) | Modeling | 6.4 |  |  |  |  | 8
Harshita Saini
Harshitha Shankar
Harshitha Shankar
Harshitha Shankar
I Jed Felix | TCCC -Ecom Phase 1 (55 Models) |  | 20 |  |  |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 20
I Jed Felix | TCCC -Ecom Phase 2 (40 Models) |  | 20 |  |  |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 20
I Jed Felix
Jagruti Khatri | Colgate_UK_4MMM_Nov2022 | Data processing | 16 |  |  |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 20
Jagruti Khatri | Colgate_Israel_4MMM_Nov2022 | Data processing | 16 |  |  |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 20
Jagruti Khatri
Jaijo Johnson Mannpuram
Jaijo Johnson Mannpuram
Jaijo Johnson Mannpuram
Janarthanam M.
Janarthanam M.
Janarthanam M.
Jeevithaa S.
Jeevithaa S.
Jeevithaa S.
Joohi Rana | Mondelez_UAE_CDM_MMM_July2022 |  | 40 |  |  |  |  | 40 |  |  |  |  | 40 |  |  |  |  | 40
Joohi Rana
Joohi Rana
Jyothsana M. Rao | US_Mizkan_11Omnichannel_2023 |  | 40 |  |  |  |  | 40 |  |  |  |  | 40 |  |  |  |  | 40
Jyothsana M. Rao
Jyothsana M. Rao
Kamalakannan M | PH_Globe_Sept2022 | Data Collection | 32 |  |  |  |  | 40 |  |  |  |  | 40 |  |  |  |  | 40
Kamalakannan M
Kamalakannan M
Karan Kumar Rijwani
Karan Kumar Rijwani
Karan Kumar Rijwani
Karthik Grandhi
Karthik Grandhi
Karthik Grandhi
Kartikaya Sahu
Kartikaya Sahu
Kartikaya Sahu
Kavya H Bhat | Topgames | KT | 20 |  |  |  | KT | 12
Kavya H Bhat | Ftoable | KT | 5 |  |  |  | KT | 8
Kavya H Bhat | Stone | Deepdives | 10 |  |  |  | Deepdives | 0
Kavya H Bhat | KCC_EMEA_MMM_3FTE_Jan2023 | Review | 8 |  |  |  | DataReview | 20 |  |  |  | Modelling | 40 |  |  |  | Modelling | 40
Keerthana Sreenivasan | Umami & Dona Gusta | Project Kick off | 32 |  |  |  |  | 40 |  |  |  |  | 40 |  |  |  |  | 40
Keerthana Sreenivasan
Keerthana Sreenivasan
Khyati Trivedi | KCC_EMEA_MMM_3FTE_Jan2023 | Data Collection
Khyati Trivedi | KCC_EMEA_MMM_3FTE_Jan2023 | Data Review
Khyati Trivedi | KCC_EMEA_MMM_3FTE_Jan2023 | Data processing
Lekha Janardhan
Lekha Janardhan
Lekha Janardhan
Manjeet Singh Rawat | L'Oreal Kiehl's | Modeling | 16 |  |  |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 20
Manjeet Singh Rawat | Umami Seasoning | Project Kick off | 16 |  |  |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 20
Manjeet Singh Rawat
Mansi Ashokkumar Choksi | Colgate_Columbia_12MMM_OralCare_April2022 | Simulation | 6.4 |  |  |  |  | 8 |  |  |  |  | 8 |  |  |  |  | 8
Mansi Ashokkumar Choksi | Colgate_Philippines_4MMM_Sept2022 | Data processing | 25.6 |  |  |  |  | 32 |  |  |  |  | 32 |  |  |  |  | 32
Mansi Ashokkumar Choksi
Manthan Sanjay Buddhbhatti
Manthan Sanjay Buddhbhatti
Manthan Sanjay Buddhbhatti
Mayank Agarwal
Mayank Agarwal
Mayank Agarwal
Mohammad Mohideen S
Mohammad Mohideen S
Mohammad Mohideen S
Mou Majumder | Colgate_Brazil_6MMM_June2022 | Modeling | 22.4 |  |  |  |  | 28 |  |  |  |  | 28 |  |  |  |  | 28
Mou Majumder | Colgate_Poland_OralCare_9MMM_Dec2022 | Data processing | 9.6 |  |  |  |  | 12 |  |  |  |  | 12 |  |  |  |  | 12
Mou Majumder
Muhammad Washif Ashraf
Muhammad Washif Ashraf
Muhammad Washif Ashraf
Naveen Chhatwani | Brazil_Nivea_POC_Dec_2022 |  | 40 |  |  |  |  | 40 |  |  |  |  | 40 |  |  |  |  | 40
Naveen Chhatwani
Naveen Chhatwani
Neeraj Choudhari
Neeraj Choudhari
Neeraj Choudhari
Neha Shaikh
Neha Shaikh
Neha Shaikh
Nishant Yadav | Mondelez_Chile_Oreo_MMMLite_Dec2022 | Modeling | 6.4 |  |  |  |  | 8 |  |  |  |  | 8 |  |  |  |  | 8
Nishant Yadav | Mondelez_UAE_Oreo_MMM_Oct2022 | Modeling | 25.6 |  |  |  |  | 32 |  |  |  |  | 32 |  |  |  |  | 32
Nishant Yadav
Nitin Wangnoo | Charlotte_Tilbury_MMM_August_2022 | Modeling | 16 |  |  |  |  | 20
Nitin Wangnoo | PH_Globe_Sept2022 | Data Collection | 16 |  |  |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 20
Nitin Wangnoo
Palak Kumar
Palak Kumar
Palak Kumar
Palak Moolchand Jain | PH_Globe_Sept2022 | Data Collection | 16 |  |  |  |  | 40 |  |  |  |  | 40 |  |  |  |  | 20
Palak Moolchand Jain
Palak Moolchand Jain
Pourav Kumar Sahoo
Pourav Kumar Sahoo
Pourav Kumar Sahoo
Pramod Moolachery
Pramod Moolachery
Pramod Moolachery
Pratap Selvan Mudaliar | Umami Seasoning | Project Kick off | 32 |  |  |  |  | 40 |  |  |  |  | 40 |  |  |  |  | 40
Pratap Selvan Mudaliar
Pratap Selvan Mudaliar
Pratheba Venkatesan
Pratheba Venkatesan
Pratheba Venkatesan
PRERANA H SULIBHAVI
PRERANA H SULIBHAVI
PRERANA H SULIBHAVI
Priyadharshni Gopinath | Brazil_Nivea_POC_Dec_2022 |  | 40 |  |  |  |  | 40 |  |  |  |  | 40 |  |  |  |  | 40
Priyadharshni Gopinath
Priyadharshni Gopinath
Rajavarman Venugopal
Rajavarman Venugopal
Rajavarman Venugopal
Rohan I Ail | USA_FB_Pundit_1MMM_Nov2022 | Modeling | 24 |  |  |  |  | 30 |  |  |  |  | 30
Rohan I Ail
Rohan I Ail
Rujul Parekh | 6 Brands refresh | Data Collection | 6.4 |  |  |  |  | 8
Rujul Parekh | Aji-ngon (PNP & MMMM) | Modeling | 12.8 |  |  |  |  | 24 |  |  |  |  | 24
Rujul Parekh | Umami & Dona Gusta | Project Kick off | 12.8 |  |  |  |  | 16 |  |  |  |  | 16 |  |  |  |  | 16
Sachin Kumar Pal | FB_Poland_Eobuwie_MMM_2022 | Modeling | 16 |  |  |  |  | 20
Sachin Kumar Pal | Turkey_Hepsiburada_1MMM_July2022 | Data Review | 16 |  |  |  |  | 20
Sachin Kumar Pal
Sanjukta Ray
Sanjukta Ray
Sanjukta Ray
Santhosh Saran
Santhosh Saran
Santhosh Saran
Santosh Nair
Santosh Nair
Santosh Nair
Sashank Ramesh
Sashank Ramesh
Sashank Ramesh
Sekar Subramanian
Sekar Subramanian
Sekar Subramanian
Shaswat Mohapatra
Shaswat Mohapatra
Shaswat Mohapatra
Shilpa Shibu
Shilpa Shibu
Shilpa Shibu
Shreya Saluja | Rosdee & Birdee | Data processing | 16 |  |  |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 20
Shreya Saluja | Reduced Salt - 2 models | Project Kick off | 3.2 |  |  |  |  | 4
Shreya Saluja | Melia | Modeling | 6.4 |  |  |  |  | 8
Shreya Saluja | Tenen | Modeling | 6.4 |  |  |  |  | 8
Shreyas Manjappa | 6 Brands refresh | Data Collection | 16 |  |  |  |  | 20
Shreyas Manjappa | Knorr | Project Kick off | 16 |  |  |  |  | 20 |  |  |  |  | 40 |  |  |  |  | 40
Shreyas Manjappa
Siddharth Kaithwas
Siddharth Kaithwas
Siddharth Kaithwas
Soham Girish Chandratre | Kimberly Clart Australia Huggies | Data processing | 12.8 |  |  |  |  | 16 |  |  |  |  | 16 |  |  |  |  | 16
Soham Girish Chandratre | Kimberly Clark Australia UBK 2022 | Data processing | 3.2 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 4
Soham Girish Chandratre | Mondelez_Chile_Oreo_MMMLite_Dec2022 | Modeling | 6.4 |  |  |  |  | 8 |  |  |  |  | 8 |  |  |  |  | 8
Soham Girish Chandratre | Colgate_Israel_4MMM_Nov2022 | Data processing | 12.8 |  |  |  |  | 16 |  |  |  |  | 16 |  |  |  |  | 16
Sravya Sri | Colgate_Israel_4MMM_Nov2022 | Data processing | 12.8 |  |  |  |  | 16 |  |  |  |  | 16 |  |  |  |  | 16
Sravya Sri
Sravya Sri
Sri Balu | Reduced Salt - 2 models | Project Kick off | 32 |  |  |  |  | 40
Sri Balu
Sri Balu
Srilakshmi Gannamaneni
Srilakshmi Gannamaneni
Srilakshmi Gannamaneni
Sudarsane G
Sudarsane G
Sudarsane G
Sumanta Singha Roy
Sumanta Singha Roy
Sumanta Singha Roy
Suresu Kumar
Suresu Kumar
Suresu Kumar
Tejasvita Saran
Tejasvita Saran
Tejasvita Saran
Umarfarookh Daval Nadaf | Topgames | Modeling | 12.8
Umarfarookh Daval Nadaf | Ftoable | Modeling | 12.8 |  |  |  |  | 16
Umarfarookh Daval Nadaf | OLX Auto (2 Regions) | Data Collection | 6.4 |  |  |  |  | 8
Umarfarookh Daval Nadaf | Mamaearth | Data Collection | 6.4 |  |  |  |  | 8
Vaibhav Dalakoti | Soup Deli | Project Kick off | 16 |  |  |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 20
Vaibhav Dalakoti | Nexon | Modeling | 16 |  |  |  |  | 20
Vaibhav Dalakoti
Vaibhav Saraswat
Vaibhav Saraswat
Vaibhav Saraswat
Varsini A S
Varsini A S
Varsini A S
Vijay Ratnakar Dakarapu
Vijay Ratnakar Dakarapu
Vijay Ratnakar Dakarapu
Vikramaditya Mishra
Vikramaditya Mishra
Vikramaditya Mishra
Vincent Abraham
Vincent Abraham
Vincent Abraham
Yokesh Devaraj
Yokesh Devaraj
Yokesh Devaraj
1 Brand | 1 BrandTotal |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
3-Winter Brands (Hotpot,Knorr, & Soup Deli) | 3-Winter Brands (Hotpot,Knorr, & Soup Deli)Total |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
6 Brands | 6 BrandsTotal |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
6 Brands refresh | 6 Brands refreshTotal |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Aji-ngon (PNP & MMMM) | Aji-ngon (PNP & MMMM)Total |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
AUS_Fantastic_furniture_MMM_Mar_2022 | AUS_Fantastic_furniture_MMM_Mar_2022Total |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
BMW JP | BMW JPTotal |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Charlotte_Tilbury_MMM_August_2022 | Charlotte_Tilbury_MMM_August_2022Total | Modeling | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
CookDo | CookDoTotal | Modeling | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
FB - River Game - Top War AOS MMM Sep2022 | FB - River Game - Top War AOS MMM Sep2022Total | Modeling | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
FB_France_Luko_MMM_Sep_2022 | FB_France_Luko_MMM_Sep_2022Total | Data Collection | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
FB_Freshly_Cosmetics_MMM_2022 | FB_Freshly_Cosmetics_MMM_2022Total | Modeling | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
FB_Oechsle_Peru_1MMM_Feb2022 | FB_Oechsle_Peru_1MMM_Feb2022Total | Data processing | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
FB_Poland_Eobuwie_MMM_2022 | FB_Poland_Eobuwie_MMM_2022Total |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Frozen Food 2 Brands | Frozen Food 2 BrandsTotal | Project Kick off | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Frozen Food 2 Brands (Model Update) | Frozen Food 2 Brands (Model Update)Total | Project Kick off | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Ftoable | FtoableTotal | Modeling | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Headway_MMM_Aug_2022 | Headway_MMM_Aug_2022Total |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
HOTPOT | HOTPOTTotal | Project Kick off | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Jollibee | JollibeeTotal | Project Kick off | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Knorr | KnorrTotal |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
L'Oreal Kiehl's | L'Oreal Kiehl'sTotal | Project Kick off | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Mamaearth | MamaearthTotal |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Melia | MeliaTotal |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Nestle 2 brands Full MMM + BE models | Nestle 2 brands Full MMM + BE models Total |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Nexon | NexonTotal | Modeling | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
OLX Auto (2 Regions) | OLX Auto (2 Regions)Total | Modeling | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Palsweet (Nov Update) | Palsweet (Nov Update)Total | Modeling | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PH_Globe_Sept2022 | PH_Globe_Sept2022Total |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Reduced Salt - 2 models | Reduced Salt - 2 modelsTotal | Modeling | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Rosdee & Birdee | Rosdee & BirdeeTotal | Modeling | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Soup Deli | Soup DeliTotal | Data Collection | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Stone | StoneTotal | Data Review | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Tenen | TenenTotal | Modeling | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Topgames | TopgamesTotal |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Turkey_Hepsiburada_1MMM_July2022 | Turkey_Hepsiburada_1MMM_July2022Total | Modeling | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Umami & Dona Gusta | Umami & Dona GustaTotal | Data Collection | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Umami Seasoning | Umami SeasoningTotal | Data Collection | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
USA_FB_Pundit_1MMM_Nov2022 | USA_FB_Pundit_1MMM_Nov2022Total |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Kimberly Clart Australia Huggies | Kimberly Clart Australia HuggiesTotal
Colgate_Columbia_12MMM_OralCare_April2022 | Colgate_Columbia_12MMM_OralCare_April2022Total
Colgate_Brazil_6MMM_June2022 | Colgate_Brazil_6MMM_June2022Total
Colgate_Philippines_4MMM_Sept2022 | Colgate_Philippines_4MMM_Sept2022Total
Colgate_UK_4MMM_Nov2022 | Colgate_UK_4MMM_Nov2022Total
Colgate_Israel_4MMM_Nov2022 | Colgate_Israel_4MMM_Nov2022Total
Mondelez_Chile_Oreo_MMMLite_Dec2022 | Mondelez_Chile_Oreo_MMMLite_Dec2022Total
Colgate_Poland_OralCare_9MMM_Dec2022 | Colgate_Poland_OralCare_9MMM_Dec2022Total
Mondelez_UAE_Oreo_MMM_Oct2022 | Mondelez_UAE_Oreo_MMM_Oct2022Total
Kimberly Clark Australia UBK 2022 | Kimberly Clark Australia UBK 2022Total
Brazil_Nivea_POC_Dec_2022 | Brazil_Nivea_POC_Dec_2022Total
US_Mizkan_3MMM_2Penetration_Sept2021 | US_Mizkan_3MMM_2Penetration_Sept2021Total
TCCC -Ecom Phase 1 (55 Models) | TCCC -Ecom Phase 1 (55 Models)Total
TCCC -Ecom Phase 2 (40 Models) | TCCC -Ecom Phase 2 (40 Models)Total
Mondelez_UAE_CDM_MMM_July2022 | Mondelez_UAE_CDM_MMM_July2022Total
US_Mizkan_11Omnichannel_2023 | US_Mizkan_11Omnichannel_2023Total